## Sheet1
Financial Analysis for Web Publishing System
Created by: Mohamed Adel Lotfy |  | Date: | 2022-12-20
Discount rate | 7%
Year
| 0 | 1 | 2 | 3 | 4 | 5
Costs | 830171 | 116160 | 127776 | 140553 | 154608 | 170068 | Total
Discount factor | 1 | 0.93 | 0.87 | 0.82 | 0.72 | 0.65
Discounted costs | 830171 | 108028.8 | 111165.12 | 115253.46 | 111317.76 | 110544.2
1386480.34
Gains | 370000 | 430000 | 420000 | 210000 | 304500 | 500000
Discount factor | 1 | 0.93 | 0.87 | 0.82 | 0.72 | 0.65
Discounted Gains | 370000 | 399900 | 365400 | 172200 | 219240 | 325000
1851740
Discounted gains - costs | -460171 | 291871.2 | 254234.88 | 56946.54 | 107922.24 | 214455.8
Cumulative gains - costs | -460171 | -168299.8 | 85935.08 | 142881.62 | 250803.86 | 465259.66 | 465259.66 | NPV
ROI | 33.56%
Payback in Year 2
Assumptions
Enter assumptions here | 1- The project is completed in year 0
2- Initial costs (year 0) are the costs of buying the server and paying for the development
3- Each year the cost increases as there is an annual increase in the salary of the editor by 10% of the base salary ($8.8k per month or $105,600 per year)
and Access database costs $130 per month or $1400 per year
4- Cost of buying a server (Hardware) is $50,000
5- Front-End and Back-End developers take $70 per hour so the total of their (four developers) payment is $250,936
6- Project manager takes $65 per hour so the total payment for his four months of work is $30,472
7- Database Analyst takes $75 per hour so the total of their (two employees) payment is $67,200
8- Security engineer takes $55 per hour so the total payment for his two months of work is $18,480
9- Domain Analyst takes $75 per hour so the total payment for his month $12,000
10- Cost of buying the Licensed softwares is $4,060
11- Cost of Software Development (See the cost estimate document for details) is $224,280
12- Cost of testing is 10% of the total hardware and software costs is $65,743
13- Total of project cost is the summation of all the previous costs = $723,171
14- This is a financial analysis for the whole project, its costs and benefits, the development company will benefit from the software development money $224,280, while the client will benefit from the NPV $465,260